ANNEX 6

WORLD AIR GAMES – STRUCTURE DOCUMENT

This document has been prepared by the FAI World Air Games Coordinating Committee.  Its purpose is to define the basic structure of the World Air Games, and to provide all interested parties with the FAI-approved framework for organizing, conducting, publicizing, financing, and governing the World Air Games.  Included herein are the general WAG responsibilities for the Organizer and FAI, the functional relationship between these two parties, and the bidding process for hosting the World Air Games.

- INTRODUCTION

The World Air Games (WAG), conducted under the guardianship of the Fédération Aéronautique Internationale (FAI), is the premier international air sports event – fielding the world’s top air sports athletes.  The World Air Games Program may consist of any, or all, of the following air sports:  Aerobatics, Aeromodelling, Ballooning, Formula-1 Pylon Racing, Gliding, Hang Gliding, Helicopters, Microlights, Para-Gliding, Parachuting, and Skydiving.

The FAI contracts an independent event organizer to conduct each WAG.  Within the WAG framework established in this document, parties bidding to host the World Air Games are encouraged to develop visionary proposals that can enhance the scope, presentation, and marketing of the WAG.

- Role and Authority of FAI

The Federation Aéronautique Internationale, founded in 1905, is the world-wide organization governing air sports, and other aeronautical and astronautical activities.  FAI’s members are national aeronautical organizations, with a membership exceeding 100 nations.  The purpose of FAI is to certify all world records for aeronautics and astronautics, to govern all international air sports competitions, and to promote air sports throughout the world.  FAI owns all rights to the World Air Games.

- Purpose of World Air Games

- The World Air Games are conducted to determine champions in all WAG sporting events, develop camaraderie among the world’s top air sports athletes, showcase air sports to the public, promote public participation in air sports, and generate revenues for the WAG Organizers and FAI.

- History of the World Air Games

The first World Air Games took place in Turkey (1997), and the second World Air Games took place in Spain (2001).  Both events included approximately 3500 participants, with 2000 athletes competing in 20+ air sports events, at eight separate competition venues.

- Organizational Structure for World Air Games

- The WAG organizational structure consists of several key elements:  Technical, Financial, Publicity, Management, Operational, Governance, and Bidding for the Games.  The WAG Organizer and FAI are inextricably linked to all of these elements – and all of these elements are linked to one another.

- The Technical element consists of the WAG Program, venues, facilities and equipment for conducting the events, presentation of the events to spectators, and logistics for the participants.  The Financial element consists of all fiscal and marketing aspects of the WAG.  The Publicity element consists of all media exposure related to the WAG.

- The Management element consists of the infrastructure and communications aspects of the WAG.  The Operational element consists of all activities related to conducting the WAG.  The Governance element consists of all legal matters relating to the WAG, including formal agreements and governing documents.  The Bidding element outlines the process for bidding to host a World Air Games.

- TECHNICAL  ELEMENT

Scope and Framework of WAG Program

The WAG Program is to be proposed by the prospective WAG Organizer in the Bid Process.  It should consist of a balanced and representative number of approved WAG events, with an absolute maximum of 1000 participants.  The World Air Games should take place over a period of six to seven days.  The Opening Ceremonies should take place on a weekend at a central venue.  The competition events should be conducted on a time-share basis at two or three venues in close proximity to one another.

- Competition Events

- FAI’s nine Air Sport Commissions (ASCs) govern the WAG events.  Collectively, the ASCs have approved 30+ air sports events for inclusion in the WAG Program.  An Event Dossier is prepared for each event by the respective ASC.  The dossier provides a description of the event, the anticipated number of event participants, and the approximate amount of technical support, operational costs, and support personnel who are required to organize, conduct, score, and present the event.

- During the Bid Process, prospective WAG organizers and ASCs should collaborate to determine which events will be proposed for inclusion in the WAG.  The WAG Program should consist of a majority of approved events, representing a majority of ASCs.  The FAI is receptive to proposals for additional air sports events from prospective WAG Organizers, if these events are approved by the ASC responsible for governing the air sport disciplines involved.

- Public Presentation of Competition Events

- WAG competition events should be presented to the on-site spectators via professional announcers, aerial video images, large video screens, and/or athlete interviews, as designated by the respective ASCs.  Olympic-style awards presentations should be conducted on-site, at the conclusion of each event.  Printed programs should provide information for each venue, including diagrams of the staging and display areas, time schedules for events, a description of each event and its objective, and competitor profiles for the top ranked athletes.  ASCs should collaborate with the WAG Organizer to provide the athlete profiles.

- Interactive Activities for the Public

- To enhance spectator interest and attendance, each participating ASC should collaborate with the WAG Organizer to provide static displays of the aircraft, sports equipment, and safety devices being used by their athletes during the WAG.  ASCs should provide materials and personnel for equipping an on-site information booth featuring its air sport disciplines.  Materials should include literature, photos, video images, etc.  Technical experts and top athletes from each discipline should staff the booths.  The WAG Organizer should provide the booth structures, furnishings, electricity, and technical support as required.

- WAG Venues

- The WAG should take place in relative close proximity to one or more large population centers, at a relatively low field elevation, during a season with a favorable climate of clear skies and low winds.

- Ideally, all WAG events should take place at one Central Airfield, a second flatland airfield, and a mountainous venue.  Within practical limitations, the closer the venues are to one another, the easier it should be to conduct the events and attract spectators to these events.  The mountainous venue will be required for hang gliding and paragliding events, but this venue should be close enough to the central airfield to accommodate all WAG participants within one centralized location.

- In addition, an Auxiliary Field should be established in the general proximity of the central airfield to serve as a rehearsal and/or preparation area, which would be available for participants throughout the WAG.  It is not mandatory that this auxiliary field be an airfield.  It could be used by disciplines such as aeromodelling, gliders, helicopters, microlights, and skydiving.

- It is necessary that the airspace required to conduct the WAG activities at each venue be available at all times during the WAG period.  Ideally, this airspace would be reserved (or, at a minimum, be prioritized) for WAG activities during this period, including pre-event WAG activities.  A collaborative working relationship should be maintained between the WAG Organizer and the authorities governing airspace.

- Depending on the events to be staged at each venue, appropriate facilities should be provided, such as:  long hard-surface runway, hard-surface ramp, grass runway, open areas with no obstructions, aircraft fuel, buildings (or tents) equipped with tables, chairs, ample electricity, and internet access.

- All venues should be well prepared for accommodating spectators by providing parking areas with efficient traffic flow, an effective means of controlling public access to and from designated areas, a well-functioning public address system, ample eating and drinking concessions, sanitary public facilities, staffed information booths, internet cafés, and options for transportation between venues.

- The central airfield should have a large hard-surface ramp area for static displays, and one or more large open hangars for indoor aeromodelling events and display booths.  The mountain venue should be free of wires, have a large obstacle-free launch site approximately 1000+ meters above a large clear landing / spectator area, and have an easily navigable safe road between the landing area and the launch site.  All venues should have large attractive areas suitable for sponsors’ hospitality tents.

- Schedule of Events

- The Schedule of Events should be determined via collaboration with the WAG Organizer, FAI’s WAG representatives, and the ASCs – based on the available facilities at each venue.  Ideally, venues should be used on a time-share basis, by assigning performance windows throughout each day for various events.

- The sequencing and duration of each performance window should be based on the needs for preparing, launching, performing, landing, and clearing the field for each specific event, as well as taking into consideration any limitations an event may have due to meteorological conditions.  A sample of a practical Daily Event Schedule and a complete WAG Schedule should be provided in the Bid Package.

- Opening Ceremonies

- The Opening Ceremonies should take place on a weekend to attract a maximum number of spectators.  The venue should be an open area, like a low stadium or airfield with seating, and be large enough to include 1000 participants parading around the infield.  Following the Parade of Athletes and formalities, a show segment should be included.  If practical, this show segment should include WAG air sports exhibitions, a WAG head-to-head competition event, and/or the start of a long-distance WAG event.

- Closing Event

- Rather than stage an elaborate closing ceremony for the public, a low-key farewell celebration should be held for the participants.  It could include snack buffets, cash bars, WAG video highlights, and basic entertainment.  Guest passes should be provided to sponsors, VIPs, and the media.

- Logistics

- The Organizer should ensure that there are adequate facilities to house, feed, and transport all WAG participants by providing a complete accommodations package.  This package should include options for several levels of accommodation, from deluxe hotels to camping facilities, to accommodate the wide range of preferred choices among WAG participants.  Mid-day meals should be served at the venues.

Safety

To minimize the risk of accidents, all FAI events are subject to stringent safety regulations.  The WAG Organizer must be acutely aware of the safety issues for each event, and always enforce safe operating procedures during the competition events and the training periods before the competition starts.

Security

- The WAG Organizer should prepare a detailed Security Plan that provides comprehensive security for all WAG participants, spectators, aircraft, and facilities.  On behalf of the Organizer, FAI will appoint a security liaison officer who is a security professional specializing in international event organization.

FINANCIAL  ELEMENT

The WAG Organizer is responsible for funding the preparation, conduct, and publicity of the entire event.  The WAG bid process requires the prospective Organizer to submit a detailed Business Plan which is to be used as the framework for financing the WAG.  This Plan must include a comprehensive Budget based on sound marketing strategies, principles, and practices.  It should clearly indicate that the prospective Organizer has a thorough understanding of the financial aspects involved in organizing a WAG.

Marketing

Organizing the World Air Games has the potential to generate considerable revenues over expenses, if the event is marketed professionally.  The WAG provides a good opportunity to reduce overhead expenses by attracting support from government entities.  Municipalities typically lend support to projects that infuse money into their economy and provide positive media exposure for the whole region.

The WAG also provides a good opportunity to generate tangible revenues.  Sponsors need exposure, and TV audiences are especially attracted to the dynamic 3-dimentional action delivered by air sports competitions.  Live aerial shows are well known for attracting large crowds of spectators, and sponsors area attracted to this kind of exposure too.  In addition, spectator fees (entrance and parking), licensing fees (food, drink, aircraft rides), and merchandizing can significantly add to these revenues.

Revenues generated from marketing the World Air Games are to be shared between the WAG Organizer and the FAI, based on a mutually approved agreement developed during the Bid Process.

Participant Fees

A WAG bid that requires no participant fees would be very well received.  However, the FAI does not prohibit the collection of participant fees as a supplemental source of revenue for the WAG Organizer.

Participant fees should have a two-tiered structure.  If the Organizer’s Business Plan calls for participant fees to be paid, all participants (athletes, coaches, and delegation officials) should pay a fixed Registration Fee.  During the Bid Process, bidders may discuss the amount of the proposed Registration Fee with FAI, but should finalize the proposed Registration Fees in their Phase 2 bid.

In addition, athletes may be asked to pay a variable Entry Fee, based on the relative cost of conducting their specific event.  The ASC should state the maximum acceptable Entry Fee in the Dossier for each event.  If the acceptable Entry Fee for an event is too low, a bidder may chose not to include that event in the proposed WAG Program.  Bidders may negotiate the Entry Fees with ASCs during the Bid Process, but should finalize the proposed Entry Fees and WAG Program in their Phase 2 bid.

Once a WAG Organizer has been selected by FAI, and the WAG Organizer Agreement has been signed, there should be no changes to the amounts of Registration Fees or Entry Fees.

Event-related Expenses

Event Dossiers contain data on the cost of conducting WAG events, including required venue structures, event-related transportation, aircraft fuel types and quantities, technicians, technical equipment, etc.  Additional expense-related information could be obtained by contacting previous event organizers for the various WAG events.  FAI has many of these contacts on file.  Ultimately, however, it is the prospective WAG Organizer who must project the probable cost of conducting these events during a WAG.

Organizer’s Fees

Each entity bidding to host a WAG will pay a non-refundable Bid Fee for Phase 1 of the Bid Process.  FAI will use these monies to prepare a Bid Review, based on an analysis of the proposed bid – including a comparison of the bid proposals with the criteria provided in the WAG Structure Document.

Each entity continuing to Phase 2 will pay a second non-refundable Bid Fee.  FAI will use these funds for on-site inspections, thorough evaluation of the materials submitted by the bidder, consulting with the bidder, and other activities FAI deems appropriate to conduct a final comprehensive evaluation of the bid.

When a bidder is selected to Organize the World Air Games, the Organizer will pay a non-refundable WAG Organizers Fee to FAI for the right to host the World Air Games.

Liability

The WAG Organizer should ensure that a comprehensive indemnification standard is in force throughout the period of organizing and conducting the WAG.

- PUBLICITY  ELEMENT

WAG Publicity involves all aspects of presenting the World Air Games to the public, and is achieved primarily through Public Relations, Advertising, News Media, and TV Programming.  A well planned and executed publicity campaign is vital to the success of the World Air Games.  The WAG Organizer should contract the services of well-established professionals in the sports marketing field to develop and implement this fundamental WAG element.

Public Relations and Advertising

Most people living in the WAG region and surrounding areas should be well informed about the WAG before it starts.  WAG banners and posters should be on display throughout these communities.  Regional TV stations and print media should be provided with professional standard video tapes and photographs of WAG air sports, and be prompted to produce segments and articles featuring the World Air Games.

An extensive Advertising campaign should focus on attracting regional spectators to the WAG events on the weekend.  Additional ads should target specific audiences to visit on designated days during the mid-week to maximize attendance, such as inviting young people for a “Youth Day” – at discount prices.

These efforts, combined with extensive News Media coverage during the WAG, should generate a great deal of positive publicity for FAI air sports and the World Air Games.  TV Programming featuring the WAG should receive extensive international distribution, which should ensure that FAI athletes are seen performing on the world stage, which promotes air sports, satisfies sponsors, and creates revenue.

Media Plan

A well developed and executed Media Plan should be a key element of the WAG Business Plan.  TV Programming and News Media coverage should be its two primary elements.  News Media coverage piques the interest of the international TV audience, and TV Programming captivates their attention.

Prior to the event, Video News Releases should be produced internally and distributed to a well-nurtured  list of media contacts.  WAG Organizers should schedule a Media Day on the day immediately prior to the start of the WAG, so News Media representatives can report on their birds-eye-views of air sports.

During the WAG, a full-featured Media Center should be provided, equipped with internet connections, private cubicles, office equipment, and an air sports media liaison to provide technical expertise.  The international media representatives on-site will be self-sufficient, but should be provided with video and photos from the WAG’s aerial cameras, along with a detailed glossary of terms to enhance their stories.

TV Programming produced during the WAG should include a daily highlights show for national and continental airing.  More-extensive TV Programming should be packaged as a series of complete shows for wide international distribution during the weeks and months following the World Air Games.

FAI’s Role in Media and Marketing

To ensure that TV producers obtain dynamic aerial images, ASCs have modified their competition rules to require pilots to shoot digital video cameras while competing.  To help sponsors, the ASCs have adopted policies that reserve ad space for sponsors on each competitor’s aircraft, flight suit, helmet, etc.

- MANAGEMENT  ELEMENT

Internal, external, and private administration:  For the sake of this document, internal refers to transactions between the WAG Organizer and FAI, or transactions within either of these parties that directly affect the other.  External refers to transactions that either party has with an outside entity.  Private internal transactions are ones that don’t affect the other party.

The Management element consists of all infrastructure and communication aspects of the WAG.  In order to ensure that the WAG is managed effectively, the WAG Organizer and FAI should establish internal management structures and procedures that allow both parties to work together cohesively.

The WAG Organizer’s infrastructure should allow it to effectively organize, conduct, and finance the World Air Games, and provide clear channels of communication with all internal and external entities.  FAI ’s infrastructure calls for its WAG Coordinating Committee (WAGCC) to serve as the formal conduit for communicating with the WAG Organizer.  The personnel representing WAGCC and WAG Organizer (by title), and their specific functions, should be designated in the WAG Governing Documents.

External Communication

During the WAG organizational period, the Organizer should maintain effective communication with all external parties involved in the WAG, including FAI Headquarters, participants, National Air Sport Controls (NACs), technical experts, government entities, professional contractors, vendors, media, the public, and all other interest parties.  Two key means that should be implemented for this purpose are a full-featured and maintained website, and an office equipped with a well-informed English speaking staff.

During the World Air Games, daily bulletins and news releases should be posted on-site, on-line, and at all accommodation sites.  At least one information center should be open at each venue during all hours of operation – stocked with programs, maps, schedules, etc., and staffed by knowledgeable interpreters.

Bulletins and Registration

Bulletins should be distributed to all NACs via posting them on the WAG website, according to a distribution schedule designated in the WAG Governing Documents.  Bulletins should include clear and comprehensive information about registering for the WAG events, accreditation procedures, accommodations, pre-event rehearsal opportunities, on-site facilities at each venue, ports-of-entry and visas, and all other information pertinent for participants who many attend the World Air Games.

OPERATIONS  ELEMENT

The WAG Organizer is responsible for coordinating, directing, and funding all operational aspects of the World Air Games.  The WAG Organizer should select all staff, and obtain use of all equipment and other materials needed for conducting the WAG, unless otherwise specified by ASCs for technical purposes.

Each ASC should approve all technical staff and equipment for its respective events.  The ASCs, in consultation with the Organizer, typically appoint or recommend the designated technical personnel, and recommend or provide the technical equipment for their respective events.  The WAG Organizer should pay the fees and expenses for these personnel and this equipment.  ASC-appointed personnel typically serve as Event Managers, Event Directors, and technical equipment operators.

Test Events

If the Organizer has limited skills in organizing certain events, an ASC may require the Organizer to conduct an on-site Test Event one year prior to the WAG.  This Test Event is a means for the Organizer to gain first-hand knowledge and experience about the operational requirements for conducting these events.

Test Events also afford the Organizer with the opportunity to identify any operational challenges which need to be resolved prior to the start of the WAG.  The ASCs should determine the need for Test Events prior to Phase 2 of the Bid Process, so the prospective Organizer can more accurately calculate the WAG Budget, and determine the proposed WAG Program.

WAG Preparation

Prior to participants arriving, WAG staff members should be familiar with, and capable of performing, all their required tasks.  Back-ups for all systems, equipment, and staff should be in place; venues should be fully prepared; volunteers should be fully trained and briefed; technical systems and equipment (and the means to run them) should be tested and fully operational; airspace clearances should be in place and functioning effectively; and operational procedures should be well rehearsed and fully functional.

During the WAG, the Organizer should run the WAG Operations as professionally, efficiently, and effectively as possible.  Any problem areas that arise should be immediately addressed and resolved.

GOVERNANCE  ELEMENT

The Governance element consists of all legal matters relating to the WAG, including formal agreements, official obligations, commitments, responsibilities, and governing documents.

The responsibilities of the WAG Organizer and the FAI, and the roles of the personnel (by title) designated to fulfill these responsibilities, should be included in the WAG Governing Documents.  These documents should also contain all other commitments agreed to by the WAG Organizer and FAI.

Milestones

The WAG Organizer and FAI should fulfill their respective obligations according to strict guidelines and protocols.  These obligations, and the schedules for fulfilling them, are collectively known as Milestones.  To monitor these Milestones, a comprehensive Milestones Timetable should be established and mutually agreed upon by the WAG Organizer and FAI, and be included in the WAG Governing Documents.

It should be the responsibility of each party to carefully monitor the progress of completing their Milestones on schedule, including those that have been tasked to third parties.  The Organizer and FAI should also monitor the progress and completion of the each other’s Milestones.  Early detection of, and attention directed toward, schedule deviations should allow for a painless resolution of such deviations.

The WAG Governing Documents include, but are not limited to, the following:

WAG Organizer Agreement:  The WAG Organizer should enter into a legal agreement with the FAI to organise, conduct, and finance the World Air Games.  This agreement will specify the rights and obligations of the two parties, and the terms and conditions for the planning and execution of the World Air Games.  This document may include specific licensing agreements, such as media and marketing agreements, or such agreements may stand on their own as separate WAG Governing Documents.

World Air Games Program:  This is the official program of WAG competition events, proposed by the WAG Organizer, and approved by FAI.

FAI Sporting Code:  This document governs all technical aspects of conducting FAI competition events.  There is one General Section, and a specialized section for the events governed by each ASC.

Competition Rules:  These documents establish the technical rules by which each WAG competition event should be conducted.  Competition Rules are written and modified by each relevant ASC.

World Anti-Doping Code:  This is the strict policy established by the World Anti-Doping Agency.

BIDDING  ELEMENT

The WAG Organizer is selected by a two-phased Bid Process.  The FAI invites any NAC, or NAC-endorced municipality, corporation, or other legal entity to bid for the right to organize and host the World Air Games.  The FAI only accepts a bid to organize the WAG if it is convinced that the bidder has the experience, desire, capabilities, and means to professionally fulfill all the obligations required of a WAG Organizer.  The FAI is not obligated to accept a bid as a result of any given WAG Bid Process.

Bid Process

For each Bid Process, the FAI publicizes a Call for Bids, and sets a deadline to receive bids at FAI Headquarters.  Bid Packages are provided to qualified entities who submit requests to FAI.  Each bidder should complete the Bid Form, prepare all additional bid documents as stipulated in the Bid Package, provide detailed information on how all the proposals included in the bid will be fulfilled, and provide any other information which the bidder believes is relevant to the bid.  Each bidder must pay a non-refundable Bid Fee to the FAI for each phase of the two-phase Bid Process in which it participates.

World Air Games Bid Package

The WAG Bid Package should include:

- Instructions for completing the WAG Bid Package

- WAG Bid Form

- WAG Structure Document

- FAI Sporting Code

- FAI-approved list of WAG Events

- ASC Event Dossiers

- Example of a WAG Schedule of Events

- World Anti-Doping Code

- Additional supporting materials

Bid Content

The basic WAG framework presented in the WAG Structure Document should be reflected in the proposed bid, with regard to the look and presentation of the World Air Games.  Enhancements to this framework are welcome and highly encouraged.  The Business Plan, marketing strategy and Media Plan should reflect a practical, yet progressive, approach to these important elements of the World Air Games.

Bid Evaluation

At the end of  Phase 1, some bids may be eliminated.  For bids that advance to Phase 2, the FAI may provide guidance on financial, technical, and media issues for which the FAI has specialized knowledge.  Site inspections and interviews should be conducted.  Clarifications and/or modifications to proposals may be requested before each bidder submits a final bid.  The FAI thoroughly evaluates all final bids in a desire to sanction one of the bidders to organize and host the next World Air Games.